## Sheet1
Quarterly Funded Projects Report
March 2026
# | Project | Sponsor | Updates | Next Steps
25-1199 M | Yakima River Mobile PIT Tag Detection Surveys | Washington Department of Fish & Wildlife | Equipment has been purchased and YN staff have been conducting sampling through the winter. High flows have pushed them out of the river multiple times, but lots of data has been gathered. | YN staff will continue to sample. Data proofing and preliminary analysis are next steps in the next couple months.
25-1189 P | SF Cowiche Creek RM 9.6-10.3 Preliminary Design | Yakama Nation | Project was cusp project and received partial funding. Sponsor plans to cover the remaining 4K through their BPA contract and budget. | YN will complete contracting.
25-1188 R | Upper Cle Elum River Riparian Restoration | Yakama Nation | 2000 plants were planted in fall 2025 following Year 1 of construction of an aquatic restoration project (a non-SRFB project being completed alongside this project), including approximately half the total anabranch plant quantities installed on the right bank, and the entire upland riparian plant zone. Approximately half of the Access and Staging plants were installed as well. 56 habitat logs were installed to aid in riparian habitat formation and protection from scour, and year 1 of seeding was completed. | Vegetation monitoring and weed treatment will occur, and the remaining 5000 plants will be installed along with the remaining habitat wood, and year 2 of seeding. Completing the right-bank planting now allows the anabranch to function as a bypass, enabling isolation and dewatering of the mainstem for ELJ installation in 2026 and eliminating the need for temporary construction access that year. Nevertheless, remobilization will still be required in 2026.
25-1187 R | SF Tieton Fish Passage at Rimrock Reservoir | Yakima County | Construction was started in fall 2025 and expected to be completed over the winter. The staging area was established, the work area was isolated, the roadway was removed and a few trees were removed and retained for reuse in the project. Excavation began on the new channel, blasting of underlying rock for the channel construction also began. Excavation is roughly 50% complete. However, in December 2025, Rimrock Reservoir experienced heavy rainfall from an atmospheric river and filled far faster than average. By January 2026, it had risen too high for construction to continue, with portions of the construction site becoming inundated. This has delayed the project until late summer or fall 2026, with project completion expected in 2027 (which would mean no need for a time extension). | The delays will raise expenses, including remobilization, and push the project schedule beyond the grant window for some of the other grants involved in this project. The sponsor will work to fill the funding gap and plan for how to complete the work in 2027. With construction on pause, Yakima County is working with the contactor to ensure that all submittals for the materials that will be used are received and reviewed prior to resuming construction. They will be monitoring reservoir conditions closely and the contractor will be called back as soon as work can resume at the site. They will be submitting bills for reimbursement for work that has already been competed on the project.
25-1186 P | Blue Slough Causeway Removal Conceptual Design | Yakima County | Project is contracted with RCO. The project lead changed. Yakima County is coordinating the project TWG. | Tidal reports will be reviewed. Yakima County is moving towards hiring contractors.
25-1185 R | Teanaway RM 5 Reforestation | Mid-Columbia Fisheries | The atmospheric river in Dec 2025 significantly altered the project site. MCF is investigating how the the project should adapt to the new lay of the land. | MCF expects to have a clearer idea of how the project should adapt by late April.
25-1184 R | West Fork Teanaway RM 7.2-8 Reforestation | Mid-Columbia Fisheries | MCF is seeking sources for the plantings. | Implementation is planned for 2027. MCF will coordinate plantings with other projects on the WF Teanaway including 24-1717.
25-1183 R | Lower Kittitas Floodplain Restoration Early Action | Mid-Columbia Fisheries | Project is contracted with RCO. Plants have been ordered. Plant costs came in slightly over budget but MCF was able to cover is under their BLM grant for the greater lower Kittias project. | The sponsor is considering a scope change to add a 1 acre subsite and herbivory deterrent fencing.
25-1182 P | Swauk & Hurley Creek Confluence Prelim Design | Mid-Columbia Fisheries | MCF initiated development of the RFP to hire a design firm. The project manager conducted an onsite evaluation with engineers to inform RFP development and identify design needs. They met with the WSDOT Development Services Lead (Transportation Engineer) to introduce the project, discuss permits, and gather requirements for restoration work adjacent to state highways. This meeting provided the Development Services Lead with the information needed to assign appropriate WSDOT staff to provide ongoing project guidance. MCF has confirmed with USFS that the project area is free of deed restrictions, liens, easements, or other encumbrances that would impede construction, operation, or maintenance. A local design team has been assembled, including representatives from the USFS, Yakama Nation, WDFW, and WSDOT. The team’s initial focus is on identifying additional advisory members, brainstorming conceptual ideas for floodplain and channel restoration, and determining roadway relocation measures. | MCF will hire a Project Manager; the position has been posted and interviews will begin soon. The team will meet to plan project steps and identify design requirements from the landowner (USFS) and adjacent landowner (WSDOT). Outreach will also be conducted to contact mining claimants within the project area to inform them of the project and ensure they are aware of the proposed restoration work. The Request for Proposals (RFP) for design services will be finalized and distributed to qualified engineering firms, with a site tour offered for interested firms. The RFP will include geotechnical testing, wetland surveys, and archaeological reporting. While the USFS has already conducted the field survey, the reporting for the project area still needs to be completed. Once selected, the design team will receive all necessary background information and site data to begin design work.
25-1179 P | Hutchinson Ranch Floodplain Conceptual Design | Kittitas Conservation Trust | Project is contracted with RCO. The property has been renamed the Hutchinson Ranch River Conservancy. | KCT will (1) perform a site assessment and conceptual analysis of the Hutchinson Ranch River Conservancy to evaluate instream, floodplain, and riparian function potential; (2) develop three restoration alternative concepts and analyze the feasibility of each proposed restoration concept (e.g. restoration concepts could include a levee setback, riparian planting, side channel reconnection, or large wood placement on Hutchinson Ranch River Conservancy); (3) develop a 30% conceptual restoration design set by December 31, 2027, that adequately details the preferred design; and (4) develop a Riparian Enhancement Plan to increase stream shading, reduce elevated summer stream temperatures, and create edge habitat for juvenile fish.
24-1816 P | Rattlesnake Creek Streamflow Improvements Design | Trout Unlimited | Culturals are complete. Trout Unlimited procured engineering and hydrogeological design consultants to prepare conceptual designs, alternatives evaluation, and preliminary designs. Trout Unlimited has begun coordination with landowners/water rights holders and introduced landowners to design consultants; the hydrogeological professional explained the need to access existing wells for groundwater survey work (use of existing wells avoids any ground disturbing activity). | TU's cultural resource consultant will complete the survey report process and address comments from state/tribal reviewers. For conceptual and preliminary designs, TU's design consultant will conduct site visits to evaluate the ground water conditions (using existing wells) and other constraints on the landscape (with feedback from the landowners). TU would like to complete the conceptual designs in 2025 and have draft preliminary designs ready for a 2026 SRFB application.
24-1810 P | Yakima River RM 156 Riparian Buffer Design | Mid-Columbia Fisheries | MCF is meeting with landowners regularly to ensure transparency and informed agreement. Site access is limited and adjacent landowners have not agreed to temporary easements to allow access; MCF is discussing implementing the riparian planting with smaller equipment, as that way site access would be possible through the main entrance of the hydro power plant. MCF drafted a landowner agreement which is awaiting approval. Cultural surveys are in progress. | Continual landowner meetings are scheduled. MCF will also reach out to property owners that share a driveway to discuss access, and continue to work to improvise site access efficiency. Regular site visits will be conducted during the project planning phase and will remain scheduled through the entire project timeline. A cultural survey firm will be contracted and cultural survey assessment and report will be initiated. MCF will determine whether to proceed with the project with the Recovery Board at the submission of the Draft alternatives assessment. They expect to complete the draft assessment by August 31st 2026 and will pause design until we get feedback from the LE on the preferred alternative.
24-1744 R | Lower Cowiche RM 1 - Stewardship 2025-2027 | Mid-Columbia Fisheries | MCF has uploaded cultural resources documentation, confirmed permit acquisition, and finalized the riparian enhancement plan. Staff conducted stewardship and maintenance of the project site, including manual weed management, herbicide application, and beaver fence maintenance and removal. Irrigation of a limited number of plants was completed throughout the summer and removed in the fall of 2025. | MCF will coordinate with landowners on 2026 stewardship priorities, primarily weed management, and conduct early-season herbicide applications to control winter annual dicots. They also plan to observe the site regularly throughout the winter for beaver herbivory.
24-1719 R | Pond 5 Reach Active Channel Planting | Yakama Nation | Wildlands has been selected as the contractor. | The original project manager took on a new position; Yakama Nation is in the process of selecting a new project manager.
24-1718 P | Middle Fork Teanaway RM 3.2 – 5.4 Design | Mid-Columbia Fisheries | MCF selected RivHab and Revive as consultants. The professional engineers at RivHab will work with the Stage 0 experts at Revive and the Forest Service Stage 0 Enterprise Team to complete the preliminary engineering and flood modeling for the project reach. Draft 30% designs have been produced and will be finalized after review by BPA and the Teanaway Forks steering committee. Upon feedback from DNR, the design team has removed road relocation elements from the design. DNR anticipates changes to the road past Indian Camp in the next five years. In September 2025, MCF staff surveyed existing vegetation throughout the project site and identified parent trees and other key resources. The riparian vegetation management strategy for this project is to promote processes that provide for natural regeneration, while protecting existing stands of key riparian species during construction where possible and planning for adaptive management through a monitoring plan. | Implementation is planned for 2028 to allow time for appropriate public engagement, permitting, and monitoring of the WF project. The 30% designs were delayed until late January due to the federal shutdown, and the team agreed on pushing the permit-level design completion and CLOMR submittal date to August 2026 to allow for spring and summer field work. The project team will complete internal review of the draft 30% design documents, then share them with BPA, SRFB technical reviewers, and the steering committee. Cultural surveys and test pits are planned for spring, along with surveys for Northern Spotted Owl habitat and further refinement of the revegetation approach. There is significant uncertainty with the federal workforce, and there is a chance that the FS staff support for this project will be removed. If this occurs, MCF will seek a cost change to expand the scope of work for the consulting engineer.
24-1717 R | West Fork Teanaway RM 6.75 - 7.2 Implementation | Mid-Columbia Fisheries | As this project was going through the SRFB grant round, alternative preliminary designs were still being completed. After visiting the site in fall 2024, some members of the project steering committee encouraged the project's WDFW engineers to explore a "Stage 0", aka "Valley Reset", design approach. In early 2025, the engineers presented a Stage 0 design. The committee has moved forward with that design and received a scope change for it. 80% designs were completed and were presented to the Recovery Board TAG/CC and State Review Panel in September 2025, and were approved. The project scope was reduced from RM 6.85-8 to RM 6.75-7.2; riparian restoration work will still occur over RM 7.2-8 under SRFB project 25-1184. Final designs have been completed. Yakama Nation Fisheries will own the construction contract for this project, and is the applicant for the project permits. MCF supported YNF in preparing permit applications for the US Army Corps of Engineers, including ESA documentation and a Least Environmentally Damaging Practicable Alternative memo. WDFW completed extensive work on the Forest Practices Application (FPA) for DNR, and DNR approved the FPA and documented a Determination of Non-Significance under SEPA in early January. FEMA returned their first round of review comments in late November. FEMA needs documentation of ESA compliance by mid-February to continue their CLOMR process. | The project construction contract is out for bid by the end of March. MCF will advertise a contract for wood provision beginning in late March concurrent with the Yakama Nation’s construction RFB. There are some permitting uncertainties related to the defunding of homeland security, but if permits come through on time construction will be in late May and wood provision will begin as soon as road conditions allow.
24-1715 R | Gold Creek Restoration RM 0.5-2 | Kittitas Conservation Trust | This project received partial funding of its Targeted Investments request, but with other funding sources is able to complete all the deliverables in RM 0.5-2 as scoped. Draft final designs for Phase I of construction are complete. Landowner permission from the USFS has been acquired, and discussions with private landowners are still ongoing. Applications for the HPA, and County Floodplain Development Permit are drafted, but need landowner signatures before we can submit. The NPDES permit will be the responsibility of the selected contractor to obtain and maintain. KCT selected KLB Construction as contractor in Oct 2025. | KCT is still working on obtaining landowner agreements for all privately owned property in the project area. If all agreements do not come through, there may be need for some level of redesign, which could cause construction delays. Mobilization is planned for Spring of 2026, as soon as the site is accessible. Staging will begin as soon as conditions allow, but construction in RM 2-3 will not occur until the in-water work window (July 15 - Semptember 30).
24-1714 A | Frog's Home Acquisition SRFB | Yakama Nation | Forterra paid the loans in full and transferred the property to the Yakama Nation in June 2025. Outside of this grant, YN has begun preparing the stewardship plan and conducting weed management activities. They are coordinating trail design with habitat restoration; partial funding for trail design has been secured from the Mellon Foundation. Wolf Water Resources was selected as design contractor and has been monitoring piezometer data and inventorying wetlands, streams, culverts, and canal features. The project leads are meeting with Reclamation and WWR to maximize habitat benefits by integrating work with adjacent Reclamation property. Grant funding for the language and cultural center design was acquired and design contracts are being developed. Conceptual designs were developed in February 2026. | There was $225k that could not be spent on the acquisition (the amount above market value for the property), so YN is determining how to use the remaining $225k. They are working on a scope change amendment request to use the balance of funds for either restoration design development or riparian restoration; expected spring 2026. Outside of this grant, planned work includes finalizing and executing design contracts for the language and cultural center, receiving and evaluating the updated cost proposal from Washington Trail Association to determine the feasible scope of trail construction, continuing coordination with Bureau of Reclamation and Wolf Water Resources on integrated habitat restoration work, proceeding with habitat and trail construction activities based on the coordinated plan developed during an October multi-agency meeting, and addressing demolition of the abandoned homesite following resolution of trespass and vandalism issues.
24-1713 R | Toppenish Creek RM 40 at Pom Pom Road (Ph II) | Yakama Nation | After the SRFB grant application was submitted and before the funding was awarded, the Slide Ranch Fire burned the restoration area. The SRFB was informed of the fire at the September 2025 funding meeting and understood there may be need for more extensive riparian restoration in conjunction with this floodplain reconnection earth work. The scope of work has been amended to include riparian and floodplain restoration after earthwork is complete--2.3 miles of streambank and 66.7 acres planted. The sponsor has put out the restoration RFP and expects to hire in Feb 2026. All rootwads for ELJs have been delivered to the project site. All spoils for plugging the existing Toppenish Creek have been delivered to the project site. A revegetation contractor has been selected for the project. Observations of natural vegetation rebound following the Slide Ranch Fire are substantial with significant signs of cottonwood and willow regeneration that will be dramatically improved with the increase in floodplain inundation expected from this project. As a result of the natural regeneration of vegetation, the sponsor has reduced the footprint of the proposed floodplain roughness treatments. | Bridge and culvert construction is funded by other sources. The contractor was hired in January and construction is scheduled to begin March 30th; this was pushed back slightly by the contractor due to the timeline for procuring bridge girders which won't be ready until June, so delaying other work made sense to avoid any gaps in the Contractor's schedule. The restoration contractor was hired in January as well. Restoration is expected to be underway starting as early as May 2026, with a completion by December 2026. There will be some temporal overlap in the construction of the bridge/culvert construction and the restoration construction but this is not expected to cause any problems.
24-1247 P | Cold Creek Passage (at Keechelus Lk) Design | Trout Unlimited | Trout Unlimited is working on permitting with state parks. Forsgren Engineering was hired. A kickoff meeting was coordinated with WA State Parks and the Engineering firm to determine Right Of Entry permit needs for the data gathering; the permit for Right of Entry has been completed and the engineer has begun data gathering. Additionally, TU worked with WA State Parks to determine level of cultural survey needed for the project. WA State Parks has already completed multiple cultural surveys in the area with known exclusion zones. | Sponsor plans to finalize data gathering and begin the alternatives assessment.
23-1220 R | Gold Creek Restoration RM 2 - 3 | Kittitas Conservation Trust | KCT applied for BOR's Water Smart Grant and received $2.3M in 2023, but this was frozen in early 2025. KCT is pursuing replacement funding through YBIP. Final designs were completed in early 2025. KCT has selected KLB Construction as their contractor. KCT will be contracting directly with Columbia Helicopters for the helicopter work, and Columbia will be working with KLB to complete work in RM 2-3. KCT investigated wood sources for the project at the nearby Swamp Lake property, but this did not work out. They are investigating other options. Applications for the HPA, and County Floodplain Development Permit are drafted, but need landowner signatures before they can submit. Section 106 has been completed by the USFS for the entire footprint of the Gold Creek Valley Restoration Project. | KCT is still working on obtaining landowner agreements for all privately owned property in the project area. If all agreements do not come through, there may be need for some level of redesign, which could cause construction delays. Mobilization is planned for Spring of 2026, as soon as the site is accessible. Staging will begin as soon as conditions allow, but construction in RM 2-3 will not occur until the in-water work window (July 15 - Semptember 30).
23-1210 P | Mid-Satus Creek Watershed Riparian Assessment | Yakama Nation | YN requested a scope change to reduce the scope of the assessment from 31.5 rivermiles (RM 7.5-39) to 8 rivermiles spilt into two separate 4-mile reaches (RM 10-14 and RM 29.5-33.5). Within these two assessment reaches piezometers were to be installed to better understand hyporheic flows and their effect on planting viability. Cramer Fish Sciences completed the initial project ID survey and habitat survey of both the upstream and downstream project reaches. In February 2026, Cramer Fish Science (CFS) completed an analysis of that data and determined that the upper extent of the assessment area (RM 29.5-33.5) could not naturally support riparian plantings, as the groundwater table is below the root zone and surface water is absent from the reach during critical flow months (approximately June through October). No piezometers will be installed in the upper reach. Moving forward, analysis of hyporheic dynamics and their relation to plant survival will be focused on the downstream reach (RMs 10-14). Several piezometers will be installed to better understand how groundwater depths vary throughout the floodplain. | YN expects to complete culturals by May; this won't be early enough to install piezometers before the spring freshet, but will be before summer low flows. Cramer Fish will install the piezometers and conduct a riparian field survey. Throughout summer 2026, CFS will start work on the riparian-process model and continue development of the HEC-RAS surface flow model. Cramer Fish will analyze the piezometer data in fall/winter 2026-27 and and start work on the groundwater model. Data analysis from all assessment components will be compiled into a final report and restoration action plan, including a reach-scale riparian enhancement plan. YN expects to complete this assessment under budget. They may be interested in adding in more site-specific riparian enhancement plans to be incorporated into restoration designs at a later time. However, this will depend on funding availability and the amount of time remaining in the grant agreement.
23-1209 P | Upper Toppenish Wood Supplementation Design II | Yakama Nation | Natural Systems Designs was selected as the design contractor to complete an assessment, design wood structures, and determine placement. Field surveys were completed and alternatives analysis completed. 15% designs have been completed; boulders were incorporated into the design as ballast for the engineered logjams. Partly owing to this addition to the design, a time extension has been requested to allow time to complete final designs in April 2026. | The deadline for the completion of preliminary designs was extended to March 31 2026. NSD will conduct another site visit to collect additional data in March (intended in February but weather did not permit); after that, preliminary designs will be completed. The cultural survey is planned after April 1, 2026 when the YRWP archaeologist has the preliminary designs. Final designs will be completed in April 2026.
23-1197 R | Teanaway River – Trust Water Rights Acq | Washington Water Trust | The original goal of project 23-1197 was to identify and bunch smaller water rights into an acquisition program that could collectively impact flow in the Teanaway River. As of May 2025, recent interactions with Teanaway water rights owners revealed some interest in the sale of water, but either at much higher prices or with a different landowner than what was provided in the original grant application. WWT is in touch with two priority project landowners and is seeking interest in permanent transactions at the price points provided in the valuation report. WWT also anticipates a scope change to add water rights transactions at another property, the Walker Ranch (Suncadia), to the project agreement. | WWT did not find a sufficient number of willing sellers from the original project list of 7 potential opportunities. WWT will close the grant incomplete as of the end of June 2026, with the balance of the funds returned to RCO. WWT is continuing a modest amount of work to support RCO's updating of their acquisitions manual to inform best practices for water acquisitions. WWT is sending final notice to all of the landowners informing them of the sunsetting of the earmarked funds, and will notify RCO immediately if strong interest unexpectedly emerges.
23-1168 R | Amon Creek, Thermal Refuge Habitat Enhancement | Benton Conservation District | Final designs were completed in August 2024. The environmental assessment, real estate license, and USACE federal permits are complete. Engineers have provided updated design cost estimates for the 100% design along with the draft construction requirements to include in the RFP. The sponsor has reached an agreement for the DNR easement allowing the low flow deflector berm. BCD secured a Riparian Grant from WSCC to support the costs of the riparian installation, and additional clearing of Russian Olives from the site. They have placed the bid for the added Russian Olive clearing, and will send out the bid for riparian plantings after the bid for the construction. Benton Conservation District worked closely with Yakama Nation Fisheries to develop the Joint Funding Agreement (JFA) between Yakama Nation (YN) and Benton CD. This JFA outlines the responsibilities of both parties, with Yakama Nation holding the construction contract for the project and Benton CD providing project oversight, onsite staff during construction, and SRFB funding to match Yakama Nation's NOAA grant that will provide just under 1 million for the project install. The JFA has been approved by Benton CD and is awaiting final signature by YN. | BCD and YN have drafted the bid documents and they are in review prior to sending the project out to bid. They anticipate the documents will be out for bid in March, pending YN timelines. The additional 5 acres of Russian Olives will be cleared in February and March from the project site using WSCC Riparian Grant Funding. BCD will finalize their contract agreement with Yakama Nation, pending signature from YN.
22-1961 + 23-1053 | Yakima River Corridor Plan Implementation Phase II | Kittitas County Public Works | The partners completed the purchase of the Yakima River RV Park in fall 2023 and began demolition at worksite 1. Technical advisory group and landowner meetings were held to review conceptual design revisions for the floodplain reconnection project, and Interfluve was hired as design contractor and developed 30% designs in Sept 2025 for worksite 2. Partner Mid-Columbia Fisheries (MCF) is conducting riparian restoration and weed treatment at worksite 3. MCF is also conducting a cottonwood pilot project at worksite 4 and monitoring seedling development; read more at https://www.midcolumbiafisheries.org/cottonwood-reforest Match funding provided in part by BLM funds routed through the Recovery Board. | Worksite 1: Cultural resources and the stewardship plan will be finalized. Buildings to be demolished will be tested for asbestos. Worksite 2: 60% designs should be complete by Jan 2026. Worksite 3: Work planning of riparian restoration Worksite 4: A summary of work, methods development, and results from 2025 will be completed. First year results will be used for work planning for 2026 pilot implementation.
22-1631 P | Whiskey Creek Barriers Design | Mid-Columbia Fisheries | This project was completed in June 2025. MCF, with WDFW, completed preliminary (60%) designs to improve fish passage at all three barriers that met both ecological and adjacent landowner objectives. This project was used as match for the FBRB project 21-1530 to complete final designs, permitting, and construction. The unspent SRFB funds were transferred to that project as well. Looking forward, there are still full passage barriers upstream of the project site; Kittitas County Public Works is aiming to address one in 2025-26. | Final report: https://secure.rco.wa.gov/prism/search/ProjectSnapshotAttachmentData.aspx?id=672690
22-1579 R | Gap to Gap Ecosystem Restoration Construction | Yakima County | Phase 1 construction (reestablishing side channels on the Sportsman's State Park Island, placing spoils in Newland Pits) was mostly completed in 2024. The Sportsman Park channels were opened in mid-Dec and flowing water was present within a week. Phase 2 (construction of the new Blue Slough headgate) began in April 2025. | Phase 3 (regrading Newland Pits as floodplain) is in the works. Yakima County is requesting another time extension--FEMA changes have created delays.
22-1571 R | River Mile 89.5 Project – Phase 2 | Yakama Nation | Final designs were submitted in fall 2024. The sponsor constructed in Sept 2025. Planting and seeding took place in October-November. | In Dec 2025, an atmospheric river caused a 20-25 year flood in the project area. The project largely worked as planned, as the flood could have been worse without it. YN is applying for a time extension to assess changes to the area from the flood that could increase future risk to property and infrastructure, and produce complete designs for any urgent repairs that are needed to maintain the function and performance of the project as designed. YN will move the spoils from the side channel excavation to the gravel pits on the north side of the Yakima River in Sept 2026 using other funding.
22-1246 A | Thorp Reach Acquisition | Kittitas Conservation Trust | KCT collaborated with its legal counsel and landowners to finalize the acquisition in early 2025. KCT and its partners are also assessing the property’s restoration potential--they completed environmental and cultural assessments and met with adjacent landowners to discuss conservation plans. They found cost savings of over $200k and will use some of the remaining funds to demolish derelict buildings, remove debris, install a new gate, complete weed treatment, and assist with relocation fees for the ag lease. The former tenant, who grew alfalfa in the pivot field, decided to stop his operations in mid 2025, as the market rate to lease the property for production was much higher than what he was paying his family before KCT acquired the property. This was unexpected and presented a weed management issue in the unfarmed field. KCT will use some of their cost savings to initiate noxious weed management with chemical and mechanical control, along with bunch grass seeding to prevent new weeds from taking hold, and received a time extension to do this in Spring 2026. KCT contractors have finalized the Relocation Plan and paid the tenants. | KCT is waiting to hear back from the RCO CR Team when the GEO 21-02 consultation is complete for the acquisition phase of the project. After cultural consultation is complete, KCT will begin clean-up of debris and fences on the property. Noxious weed management will take place this Spring.
21-1543 R | Naneum Creek at SM 3.75 | Kittitas County Conservation District | FBRB project to replace a culvert (FPDSI #602331)on Naneum Creek that creates a velocity barrier with 33% passability so a continuous, more natural stream channel can be constructed. This will restore access to 2.8 miles of habitat that has been blocked for more than a century. A 15% basis of design report is completed and 30% designs are underway, expected in October 2025. The initial cost for the engineering and design work presented by Anderson Perry & Associates in November 2024 was more than twice the amount included in the cost estimate for this grant agreement and nearly as much as is available for construction of the project. The costs are high due in part to the flood risk analysis that is now required by Kittitas County. It also appears the construction costs were underestimated based on experience with project 20-1692 (CID @ Coleman) and that without significant additional funding, construction will be delayed. Grant applications to other sources for additional construction funding are being considered. | KCCD will request a time extension and cost increase in the first half of 2026.
21-1538 P | Crystal Creek | Trout Unlimited | FBRB project. Recently finally received funding. In 2025, Trout Unlimited worked to secure landowner certifications for each of the landowners. This included coordination with the City of Roslyn, City of Cle Elum, and Kittitas County. | TU plans to create an RFQ for engineering services, put the RFQ out for bid, conduct bidding review, and complete the hiring of the engineer. TU also plans to take the hired engineer through a kickoff meeting with the various landowners to ensure upfront coordination and planning for the required land uses and flood mitigation as well as fish passable designs.
21-1530 R | Whiskey Creek Barriers, Ellensburg | Mid-Columbia Fisheries | This FBRB project applied for a cost increase in Jan 2025 due to 1) inflation and supply chain challenges, 2) increased project management needs, and 3) emergent project complexities including maintaining gradient continuity for long-term stream stability, supporting landowners with differing objectives without compromising ecological goals, and designing a bypass for an existing weir. The cost increase request was granted in May 2025. The preliminary design required extra time for review by landowners and the Technical Advisory Team before being modified through a design memo. With the TRT’s acceptance of the revised design, the project is now advancing toward the 80% and final design stages. | MCF is focusing on advancing permit-level design and initiating project permitting. They will also begin developing and submitting permit applications to regulatory agencies. Additional activities include ongoing engagement with landowners, as well as coordination with TAG members and agency partners to ensure the design continues to meet fish passage and RCO/HIP objectives. Staff will also begin preliminary planning for construction logistics, including material staging and site access, to ensure a smooth transition from design to implementation.
21-1474 R | Coleman Creek at SM 4.7 | Kittitas County Conservation District | This FBRB project is under contract as of Jan 2025. The budget was completed prior to some recent bid activities and is anticipated to be low. A cost increase request may occur, however KCCD is waiting until the engineers have an opportunity to review the design and complete a cost estimate. | Possibly applying for cost increase.
20-1693 P | EWC at Naneum Creek Fish Passage | Kittitas County Conservation District | FBRB Project. KCCD completed a scope change request to convert the project from construction to design only. Construction was not possible in 2025 (cost estimates came in at double the current amount of secured construction funding), but designs can be completed. Additional construction funding is being sought through FBRB application 26-1057. Project designs are now at 80%, with significant work completed on the flood risk analysis necessary for the Kittitas County Floodplain Development permit. There are insurable structures in the vicinity of the project, requiring a more robust analysis of the project and multiple back and forth communications with landowners and the permitting agencies. KCCD has completed an adaptive mgmt plan and is moving on to final designs. The project will have only one bridge and no diversion. | Final project designs, specifications and cost estimates will be completed. The No-Rise requirement has presented challenges; KCCD expects to have to do an inset floodplain to meet the reqs.
20-1692 R | CID at Coleman Creek Fish Screening & Passage | Kittitas County Conservation District | FBRB project to siphon the Cascade Irrigation District (CID) canal, currently a full fish passage barrier with 0% passability, under Coleman Creek so a continuous, more natural stream channel can be constructed. Additionally, a fish screen will be installed. This will restore access to 1 mile of habitat. Final designs were completed in 2024. The project was first advertised for bid in October 2024, but the bids received far exceeded the secured project funding so all bids were rejected. KCCD worked with the project manager to secure additional funding and a time extension to Oct 2026. They reissued for bid in July 2025 with reduced costs and selected a bidder at a project cost of $3.1M, which is a very tight but workable budget. | In-stream work will be completed by February 2026. Construction will be completed in March prior to CID's turn on date for the irrigation season.
20-1398 PR | Tjossem Ditch Headworks Removal and Restoration | Trout Unlimited | In 2022, TU received stakeholder feedback and had to complete new designs; TU secured additional funding through BOR. In 2025, the project experienced significant delays due to BOR layoffs. TU was able to contact a BOR staff member who is taking over the Schaake property later in 2025 which helped to answer questions needed to guide designs for the future restoration of Tjossem Ditch. TU met with their technical work group in Fall 2025 and confirmed that the levee will remain in place and the ditch will not be a functioning side channel. Preliminary designs were completed in fall 2025. TU was granted a short time extension until Jan 31 2026 to assess whether final designs and/or headgate demolition could be completed in 2026 with a longer time extension. However, when TU sent the preliminary designs to BOR for review, BOR's engineer's estimate of the costs for the headgate removal came in much higher than expected. At this time TU does not see significant cost savings that would bring the construction cost of the headgate removal down to a level that is covered within this grant or where a gap could be filled with outside funding, and will be closing the project incomplete. They will work with the BOR to secure federal funds to remove the headgate. | Section 106 is currently underway, with the US Fish and Wildlife service helping with the completion of this permit. Section 106 will not be completed before this funding is closed. TU is continuing to use BOR funding to work with engineers on the cost savings changes to the designs. Additionally, TU continues to work with the USFWS and the BOR on the permitting aspects not yet completed.
Note on D39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add description of project